## All Plans Summary
Summary of New York City Transit Capital Signal Projects
Description | Phase as of May 2017 | Original,Start | Current,Start | Original, Completion | Current, Completion | Start delay in months | Actual or anticipated completion delay in months
2005-2009 Capital Plan
Signal Control Modifications Phase 3 | Complete | 2006-06-01 | 2006-09-01 | 2011-10-01 | 2011-12-01 | 3 | 2
Signal Cable Replacement | Complete | 2005-11-01 | 2005-12-01 | 2007-08-01 | 2011-06-01 | 1 | 46
Signal Key-By Circuit Modifications Phase 2 | Complete | 2007-06-01 | 2008-12-01 | 2013-03-01 | 2014-04-01 | 18 | 13
Communications-Based Train Control Flushing Line Phase 1 | Construction | 2007 | 2010-06-01 | 2016-11-01 | 2017 | 36 | 7
Signal Modernization White Plains Road Line Phase 3: East 180th Street | Complete | 2006-06-01 | 2007-11-01 | 2011-08-01 | 2011-11-01 | 17 | 3
Interlocking 4th Avenue - Culver Line | Complete | 2009-06-01 | 2009-03-01 | 2012-09-01 | 2012-12-01 | -3 | 3
Interlockings 5th Avenue, Lexington Avenue - Queens Boulevard Line | Complete | 2008-09-01 | 2009-01-01 | 2012-05-01 | 2012-11-01 | 4 | 6
Modernize 3 Interlockings - 8th Avenue Line | Complete | 2006-04-01 | 2006-10-01 | 2009-10-01 | 2010-06-01 | 6 | 8
Communications-Based Train Control Equipment - 64 R160 Cars - Canarsie Line | Complete | 2007-07-01 | 2008-10-01 | 2008-10-01 | 2012-03-01 | 16 | 41
2010-2014 Capital Plan
Modification of Signal Control Lines - Phase 4 | Complete | 2011-08-01 | 2011-08-01 | 2013-11-01 | 2014-02-01 | 0 | 3
Modernize Signal Interlocking at Church Avenue on the Culver Line | Construction | 2010-06-01 | 2010-06-01 | 2014-08-01 | 2021 | 0 | 82
Replace Solid State Signal Equipment at 13 Locations | Complete | 2010 | 2011-05-01 | 2012-11-01 | 2015-04-01 | 11 | 29
Convert R-142 Railcars for Communications-Based Train Control on the Flushing Line | Complete | 2010 | 2011-12-01 | 2016-02-01 | 2016-06-01 | 18 | 4
Support / Removals for Communications-Based Train Control on the Flushing Line | Construction | 2010-11-01 | 2010-11-01 | 2016-11-01 | 2018 | 0 | 19
Install Station Time Signal Enhancements on the Lexington Avenue Line - Phase 2 | Complete | 2011-09-01 | 2011-09-01 | 2014-05-01 | 2014-05-01 | 0 | 0
Replace Stop Cables for Signals - Phase 4 | Complete | 2011-06-01 | 2011-06-01 | 2014-05-01 | 2013-10-01 | 0 | -7
Modernize Signal Interlockings at 71st Avenue and Union Turnpike on the Queens Boulevard Line | Construction | 2012-11-01 | 2012-11-01 | 2017-04-01 | 2018 | 0 | 14
Install Communications-Based Train Control Signals Test Track on the Culver Line - Phase 2 | Complete | 2011-09-01 | 2011-09-01 | 2015-09-01 | 2015-12-01 | 0 | 3
Modifications to Signal Control Lines - Phase 5 | Complete | 2012 | 2013-12-01 | 2015-05-01 | 2015-05-01 | 18 | 0
Modernize Signals and Interlockings on the Dyre Avenue Line | Construction | 2012 | 2013-04-01 | 2017-07-01 | 2017 | 10 | -1
Modernize Signal Interlocking at Roosevelt Avenue on the Queens Boulevard Line | Complete | 2012 | 2013-01-01 | 2016-12-01 | 2016-12-01 | 7 | 0
Modernize Signal Interlocking at 34th Street on the 6th Avenue Line | Construction | 2012 | 2014-04-01 | 2018 | 2018 | 22 | 0
Modernize Signal Interlocking at West 4th Street on the 6th Avenue Line | Construction | 2012 | 2014-07-01 | 2018 | 2018 | 25 | 0
Modification of Signal Key-By Circuits - Phase 3 | Complete | 2013 | 2014-04-01 | 2016-06-01 | 2016-06-01 | 10 | 0
Install Communication-Based Train Control on the Queens Boulevard Line West - Phase 1 | Construction | 2013 | 2015-08-01 | 2019 | 2021 | 26 | 24
Rehabilitation of Ducts and Cables, Steinway Tube | Complete | 2012-01-01 | 2012-01-01 | 2015-01-01 | 2015-09-01 | 0 | 8
Communications-Based Train Control: Equipment Supplier Interoperability | Construction | 2014 | 2015-09-01 | 2018 | 2018 | 15 | 0
Replacement of Automatic Train Supervision A-Division and Communications-Based Train Control Status Boards at the Rail Control Center | Complete | 2014-02-01 | 2014-02-01 | 2015-10-01 | 2015-10-01 | 0 | 0
Automated Train Supervision: Hardware and Software Upgrade | Complete | 2015 | 2013-05-01 | 2015 | 2016-12-01 | -25 | 18
Modernize Signal Interlockings at 4 Locations on the 6th Avenue Line - Design Only | Complete | 2014-06-01 | 2014-06-01 | 2016-06-01 | 2015-06-01 | 0 | -12
Modernize Signal Interlocking at Kings Highway on the Culver Line - Design Only | Complete | 2013-12-01 | 2013-12-01 | 2015-05-01 | 2015-05-01 | 0 | 0
AC to DC Line Relay Conversions on the Fulton Line | Complete | 2014-04-01 | 2014-04-01 | 2015-02-01 | 2015-02-01 | 0 | 0
Signal Fire Room Suppression, Phase 2 - Design Only | Design | 2015-10-01 | 2015-10-01 | 2017 | 2017 | 0 | 0
2015-2019 Capital Plan
Install Communication-Based Train Control on the Queens Boulevard Line West - Phase 2 | Construction | 2016-12-01 | 2016-12-01 |  | 2022 | 0
Communications-Based Train Control (CBTC) Technical Support Contract on the Flushing Line | Planning | 2018 | 2018 |  |  | 0
Install Communication-Based Train Control (CBTC) on the 8 Avenue Line from 59 Street to High Street | Design | 2018 | 2018 |  |  | 0
Install Automatic Signals for Work Trains on the Canarsie Line | Planning | 2016 | 2017 |  | 2021 | 12
Modernize Signal Interlocking at Ditmas Avenue on the Culver Line | Design | 2017 | 2018 |  |  | 12
Modernize Signal Interlocking at Kings Highway on the Culver Line | Construction | 2016-10-01 | 2016-10-01 |  | 2021 | 0
Modification to Signal Control Lines - Phase 6 | Construction | 2015-04-01 | 2015-04-01 |  | 2020 | 0
AC to DC Line Relay Conversion on the Fulton Line | Construction | 2015-01-01 | 2015-01-01 |  | 2017 | 0
AC to DC Line Relay Conversion on the Crosstown Line | Construction | 2017-03-01 | 2017-03-01 |  | 2021 | 0
Modification of Signal Key-By Circuits - Phase 4 | Construction | 2016-07-01 | 2016-07-01 |  | 2019 | 0
Code Cable Replacement on the Broadway-7 Avenue Line | Planning | 2019 | 2018 |  |  | -12
Signal Room Fire Suppression, Phase 2 | Design | 2017 | 2018 |  | 2020 | 12
Life Cycle Replacement of Code Systems | Planning | 2018 | 2018 |  |  | 0
Life Cycle Modification of Speed Enforcement Systems | Planning | 2018 | 2018 |  |  | 0
Upgrade 25 Hz AC Main Cable and De-Ion Switches - Design Only | Planning | 2017 | 2018 |  | 2020 | 12
Modernize Signal Interlocking at Parsons Boulevard on the Queens Boulevard Line | Planning | 2019
Eliminate Single Point Failure of Interlocking Control at 21 Locations on the A Division | Planning | 2017 | 2018 |  |  | 12
Install Communication-Based Train Control (CBTC) from Church Avenue to West 8 Street on the Culver Line | Design | 2017 | 2018 |  |  | 12
Modernize Signal Interlocking at Avenue X on the Culver Line | Design | 2017 | 2018 |  |  | 12
Signal Component Replacement | Planning | 2017 | 2019 |  |  | 24
Modernize 2 Signal Interlockings: 30 Street and 42 Street North on the 8 Avenue Line | Design | 2018 | 2018 |  |  | 0
NOTES: Current refers to May 2017. When month is not given, assumes June. For the 2015-2019 plan, only a current completion date is listed, and in many cases it is missing. Summary data excludes "supersceded" projects, which have been replaced, or subsumed inside other projects Summary data also excludes one project from the 2010-2014 plan that lacked information on current cost, current start date, and current completion date.
SOURCE: IBO analysis of Metropolitan Transportation Authority data.

## 2005-2009 Plan Details
New York City Transit Signal Projects 2005-2009 Capital Plan - Details
Description | Phase | Original Budget | Current | Current, constant 2017$ | Original,Start | Current,Start | Original, Completion | Current, Completion
Signal Control Modifications Phase 3 | Complete | 33001200 | 32066865 | 39775322.5006 | 2006-06-01 | 2006-09-01 | 2011-10-01 | 2011-12-01
Signal Cable Replacement | Complete | 18373800 | 51516285 | 63900130.2406 | 2005-11-01 | 2005-12-01 | 2007-08-01 | 2011-06-01
Signal Key-By Circuit Modifications Phase 2 | Complete | 38409600 | 28081106 | 34831438.8489 | 2007-06-01 | 2008-12-01 | 2013-03-01 | 2014-04-01
Communications-Based Train Control Flushing Line Phase 1 | Construction | 265583600 | 405723815 | 503254546.0184 | 2007 | 2010-06-01 | 2016-11-01 | 2017
Signal Modernization White Plains Road Line Phase 3: East 180th Street | Complete | 185334900 | 289614256 | 359233758.3726 | 2006-06-01 | 2007-11-01 | 2011-08-01 | 2011-11-01
Interlocking 4th Avenue - Culver Line | Complete | 222000000 | 114894344 | 142513450.7566 | 2009-06-01 | 2009-03-01 | 2012-09-01 | 2012-12-01
Interlockings 5th Avenue, Lexington Avenue - Queens Boulevard Line | Complete | 106233500 | 147000698 | 182337754.8995 | 2008-09-01 | 2009-01-01 | 2012-05-01 | 2012-11-01
Modernize 3 Interlockings - 8th Avenue Line | Complete | 55000000 | 134691025 | 167068996.5269 | 2006-04-01 | 2006-10-01 | 2009-10-01 | 2010-06-01
Communications-Based Train Control Equipment - 64 R160 Cars - Canarsie Line | Complete | 12000000 | 71394158 | 88556385.5123 | 2007-07-01 | 2008-10-01 | 2008-10-01 | 2012-03-01
NOTES: Constant 2017 dollar values calculated using IBO's actual and projected state and local government spending deflator.
SOURCE: IBO analysis of Metropolitan Transportation Authority data.

## 2010-2014 Details
New York City Transit Signal Projects 2010-2014 Capital Plan - Details
Description | Phase | Latest Amendment Budget | Current | Current, constant 2017$ | Original,Start | Current,Start | Original, Completion | Current, Completion
Modification of Signal Control Lines - Phase 4 | Complete | 25334078 | 24191268 | 26601350.3409 | 2011-08-01 | 2011-08-01 | 2013-11-01 | 2014-02-01
Replace Signal Messenger Brackets on the Brighton Line | Superseded | 1368700 |  |  | 2013
Modernize Signal Interlocking at Church Avenue on the Culver Line | Construction | 202387500 | 184784442 | 203193800.3079 | 2010-06-01 | 2010-06-01 | 2014-08-01 | 2021
Replace Solid State Signal Equipment at 13 Locations | Complete | 16253825 | 13137772 | 14446637.3433 | 2010 | 2011-05-01 | 2012-11-01 | 2015-04-01
Convert R-142 Railcars for Communications-Based Train Control on the Flushing Line | Complete | 224777244 | 224777244 | 247170930.2837 | 2010 | 2011-12-01 | 2016-02-01 | 2016-06-01
Support / Removals for Communications-Based Train Control on the Flushing Line | Construction | 164764465 | 140895099 | 154931932.0431 | 2010-11-01 | 2010-11-01 | 2016-11-01 | 2018
Install Station Time Signal Enhancements on the Lexington Avenue Line - Phase 2 | Complete | 29171306 | 27639834 | 30393483.6156 | 2011-09-01 | 2011-09-01 | 2014-05-01 | 2014-05-01
Replace Stop Cables for Signals - Phase 4 | Complete | 4777701 | 2301783 | 2531100.7258 | 2011-06-01 | 2011-06-01 | 2014-05-01 | 2013-10-01
Modernize Signal Interlockings at 71st Avenue and Union Turnpike on the Queens Boulevard Line | Construction | 310836263 | 297896714 | 327575009.8966 | 2012-11-01 | 2012-11-01 | 2017-04-01 | 2018
Install Communications-Based Train Control Signals Test Track on the Culver Line - Phase 2 | Complete | 84900000 | 84900000 | 93358258.1922 | 2011-09-01 | 2011-09-01 | 2015-09-01 | 2015-12-01
Modifications to Signal Control Lines - Phase 5 | Complete | 10000000 | 9237502 | 10157798.5485 | 2012 | 2013-12-01 | 2015-05-01 | 2015-05-01
Modernize Signals and Interlockings on the Dyre Avenue Line | Construction | 224812065 | 226121531 | 248649143.3912 | 2012 | 2013-04-01 | 2017-07-01 | 2017
Modernize Signal Interlocking at Roosevelt Avenue on the Queens Boulevard Line | Complete | 101405148 | 101355148 | 111452768.8586 | 2012 | 2013-01-01 | 2016-12-01 | 2016-12-01
Modernize Signal Interlocking at 34th Street on the 6th Avenue Line | Construction | 226361133 | 180002100 | 197935012.0959 | 2012 | 2014-04-01 | 2018 | 2018
Modernize Signal Interlocking at West 4th Street on the 6th Avenue Line | Construction | 230773069 | 174106895 | 191452490.6532 | 2012 | 2014-07-01 | 2018 | 2018
Modification of Signal Key-By Circuits - Phase 3 | Complete | 15000000 | 13562372 | 14913538.5969 | 2013 | 2014-04-01 | 2016-06-01 | 2016-06-01
Install Communication-Based Train Control on the Queens Boulevard Line West - Phase 1 | Construction | 122921000 | 117820673 | 129558690.3453 | 2013 | 2015-08-01 | 2019 | 2021
Modernize Signal Interlocking at Jay Street on the 6th Avenue Line - Design Only | Planning | 7062000 |  |  | 2014 |  | 2016
Rehabilitation of Ducts and Cables, Steinway Tube | Complete | 46499585 | 50193867 | 55194487.5742 | 2012-01-01 | 2012-01-01 | 2015-01-01 | 2015-09-01
Communications-Based Train Control: Equipment Supplier Interoperability | Construction | 1228500 | 4995209 | 5492862.3268 | 2014 | 2015-09-01 | 2018 | 2018
Replacement of Automatic Train Supervision A-Division and Communications-Based Train Control Status Boards at the Rail Control Center | Complete | 7179300 | 6631911 | 7292622.6083 | 2014-02-01 | 2014-02-01 | 2015-10-01 | 2015-10-01
Automated Train Supervision: Hardware and Software Upgrade | Complete | 5900000 | 5900000 | 6487794.15 | 2015 | 2013-05-01 | 2015 | 2016-12-01
Modernize Signal Interlockings at 4 Locations on the 6th Avenue Line - Design Only | Complete | 0 | 2787488 | 3065194.6338 | 2014-06-01 | 2014-06-01 | 2016-06-01 | 2015-06-01
Modernize Signal Interlocking at Kings Highway on the Culver Line - Design Only | Complete | 0 | 6085272 | 6691524.0818 | 2013-12-01 | 2013-12-01 | 2015-05-01 | 2015-05-01
AC to DC Line Relay Conversions on the Fulton Line | Complete | 0 | 5405279 | 5943786.0128 | 2014-04-01 | 2014-04-01 | 2015-02-01 | 2015-02-01
AC to DC Line Relay Conversion on the Fulton Line | Superseded | 0 |  |  | 2015-01-01 |  | 2017
Modifications to Signal Control Lines - Phase 6 | Superseded | 0 |  |  | 2015-04-01 |  | 2019
Signal Fire Room Suppression, Phase 2 - Design Only | Design | 0 | 639600 | 703320.8709 | 2015-10-01 | 2015-10-01 | 2017 | 2017
NOTES: Constant 2017 dollar values calculated using IBO's actual and projected state and local government spending deflator.
SOURCE: IBO analysis of Metropolitan Transportation Authority data.

## 2015-2019 Plan Details
New York City Transit Signal Projects 2015-2019 Capital Plan - Details
Description | Phase | Latest Amendment Budget | Current | Current, constant 2017$ | Original,Start | Current,Start | Original, Completion | Current, Completion
Install Communication-Based Train Control on the Queens Boulevard Line West - Phase 2 | Construction | 338225423 | 338225423 | 330072629.0622 | 2016-12-01 | 2016-12-01 |  | 2022
Communications-Based Train Control (CBTC) Technical Support Contract on the Flushing Line | Planning | 1000000 | 1000000 | 975895.384 | 2018 | 2018
Install Communication-Based Train Control (CBTC) on the 8 Avenue Line from 59 Street to High Street | Design | 539143531 | 539143531 | 526147683.2244 | 2018 | 2018
Install Automatic Signals for Work Trains on the Canarsie Line | Planning | 5000000 | 5000000 | 4879476.9201 | 2016 | 2017 |  | 2021
Modernize Signal Interlocking at Ditmas Avenue on the Culver Line | Design | 116339211 | 116339211 | 113534898.9948 | 2017 | 2018
Modernize Signal Interlocking at Kings Highway on the Culver Line | Construction | 170074017 | 170074017 | 165974448.1312 | 2016-10-01 | 2016-10-01 |  | 2021
Modernize Signal Interlocking at 30 Street on the 8 Avenue Line | Superseded | 129669871 |  |  | 2018
Modernize Signal Interlocking at 42 Street North on the 8 Avenue Line | Superseded | 119277329 |  |  | 2018
Modification to Signal Control Lines - Phase 6 | Construction | 33011628 | 33011628 | 32215895.384 | 2015-04-01 | 2015-04-01 |  | 2020
AC to DC Line Relay Conversion on the Fulton Line | Construction | 13545979 | 13545979 | 13219458.3781 | 2015-01-01 | 2015-01-01 |  | 2017
AC to DC Line Relay Conversion on the Crosstown Line | Construction | 28772170 | 25168851 | 24562165.5119 | 2017-03-01 | 2017-03-01 |  | 2021
Modification of Signal Key-By Circuits - Phase 4 | Construction | 18838735 | 18429499 | 17985263.0038 | 2016-07-01 | 2016-07-01 |  | 2019
Code Cable Replacement on the Broadway-7 Avenue Line | Planning | 7386547 | 7386547 | 7208497.1211 | 2019 | 2018
Signal Room Fire Suppression, Phase 2 | Design | 15613480 | 15613480 | 15237123.0604 | 2017 | 2018 |  | 2020
Life Cycle Replacement of Code Systems | Planning | 70423787 | 70423787 | 68726248.6581 | 2018 | 2018
Life Cycle Modification of Speed Enforcement Systems | Planning | 45000000 | 45000000 | 43915292.2807 | 2018 | 2018
Upgrade 25 Hz AC Main Cable and De-Ion Switches - Design Only | Planning | 1145471 | 1145471 | 1117859.8614 | 2017 | 2018 |  | 2020
Modernize Signal Interlocking at Parsons Boulevard on the Queens Boulevard Line | Planning | 165676806 | 165676806 | 161683230.2137 | 2019
Eliminate Single Point Failure of Interlocking Control at 21 Locations on the A Division | Planning | 10000000 | 10000000 | 9758953.8401 | 2017 | 2018
Install Communication-Based Train Control (CBTC) from Church Avenue to West 8 Street on the Culver Line | Design | 166610595 | 166610595 | 162594510.5885 | 2017 | 2018
Modernize Signal Interlocking at Avenue X on the Culver Line | Design | 146926121 | 146926121 | 143384523.2751 | 2017 | 2018
Signal Component Replacement | Planning | 10000000 | 10000000 | 9758953.8401 | 2017 | 2019
Modernize 2 Signal Interlockings: 30 Street and 42 Street North on the 8 Avenue Line | Design | 0 | 248947200 | 242946423.3434 | 2018 | 2018
NOTES: Constant 2017 dollar values calculated using IBO's actual and projected state and local government spending deflator.
SOURCE: IBO analysis of Metropolitan Transportation Authority data.